## project
| PLAN | PLAN | ACTUAL | ACTUAL | PERC | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | START | DUR | START | DUR | COMPLT | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Project Timeline | 1 | 60 | 1 | 60 | 0%
Vault | 1 | 25 | 1 | 25 | 0%
Design vault's tree structure | 1 | 2 | 1 | 2 | 0%
- Documentation | 1 | 2 | 1 | 2 | 0%
Finalize a common file structure (SF data) | 1 | 2 | 1 | 2 | 0%
- File format | 1 | 2 | 1 | 2 | 0%
- Data structure | 1 | 2 | 1 | 2 | 0%
- Meta-Data structure | 1 | 2 | 1 | 2 | 0%
- Dataset name/version conventions | 1 | 2 | 1 | 2 | 0%
- Documentionation and examples | 1 | 2 | 1 | 2 | 0%
Finalize Darwin outputs format in vault (native format+conversion code?) | 1 | 4 | 1 | 4 | 0%
- Use native model outputs? | 1 | 4 | 1 | 4 | 0%
- Coversion code to common file structure | 1 | 4 | 1 | 4 | 0%
- Code: downsample (time-space), domain cut | 1 | 4 | 1 | 4 | 0%
Utilities to validate a sample data file | 3 | 3 | 3 | 3 | 0%
Develop vault's API [DBX?] | 1 | 10 | 1 | 10 | 0%
- User authentication | 1 | 10 | 1 | 10 | 0%
- Permission contrrol | 1 | 10 | 1 | 10 | 0%
- Upload/download/remove/rename files and dirs | 1 | 10 | 1 | 10 | 0%
Populate collected files in vault | 6 | 5 | 6 | 5 | 0%
Vault's front-end [DBX?] | 8 | 10 | 8 | 10 | 0%
Prepare vault's documentations and API's sample codes | 15 | 5 | 15 | 5 | 0%
QC, test, deploy | 20 | 6 | 20 | 6 | 0%
Database | 1 | 60 | 1 | 40 | 0%
Confirm the appropriate database solution | 3 | 2 | 3 | 2 | 0%
Finalize DB host | 4 | 1 | 4 | 1 | 0%
DB design: | 5 | 1 | 5 | 1 | 0%
- Data structure | 6 | 1 | 6 | 1 | 0%
- Performance strategies (indx, partition) | 6 | 1 | 6 | 1 | 0%
- Data compression | 7 | 2 | 7 | 2 | 0%
- Data integrity | 7 | 2 | 7 | 2 | 0%
- Security | 7 | 2 | 7 | 2 | 0%
- Maintenance/ Backup/ Recovery plans | 7 | 2 | 7 | 2 | 0%
Batch insert pipeline: | 4 | 1 | 4 | 1 | 0%
- Utilities to batch insert a csv file | 5 | 1 | 5 | 1 | 0%
- Utilities to convert misclanous files (such as netcdf) to csv | 6 | 1 | 6 | 1 | 0%
Ingest selected non-Simon's Foundation-funded data (satellite?) | 6 | 1 | 6 | 1 | 0%
Ingest labs data | 7 | 2 | 7 | 2 | 0%
Apply index, compression strategies | 7 | 2 | 7 | 2 | 0%
Develop stored procedures to execute critical queries: | 7 | 2 | 7 | 2 | 0%
- Snapshot (fixed time, variable space) | 3 | 2 | 3 | 2 | 0%
- Timeseries (variable time, fixed space) | 4 | 1 | 4 | 1 | 0%
- Generic (variable time, variable space) | 5 | 1 | 5 | 1 | 0%
Prepare DB's documentations | 6 | 1 | 6 | 1 | 0%
QC and test (security, heavy loads, and extreme cenarios) | 6 | 1 | 6 | 1 | 0%
Interface | 10 | 51 | 1 | 26 | 0%
Open source libraries implementing core functions: [Python, (R, Matlab?)] | 6 | 3 | 6 | 3 | 0%
- DB connection | 6 | 3 | 6 | 3 | 0%
- Handle vault's communications (download, upload, query) | 7 | 1 | 7 | 1 | 0%
- Retrieve snapshot data (fixed time, variable space) | 8 | 4 | 8 | 4 | 0%
- Retrieve timeseries data (variable time, fixed space) | 6 | 3 | 6 | 3 | 0%
- Retrove generic distribution (variable time, variable space) | 6 | 3 | 6 | 3 | 0%
- documentation and tutorials (Python, R, Matlab) | 7 | 1 | 7 | 1 | 0%
Graphical User Interface: | 8 | 4 | 8 | 4 | 0%
- Web app | 6 | 3 | 6 | 3 | 0%
- Mac app | 6 | 3 | 6 | 3 | 0%
- Win app | 7 | 1 | 7 | 1 | 0%
* User authentication | 8 | 4 | 8 | 4 | 0%
* Vault's import/export | 6 | 3 | 6 | 3 | 0%
* Data cataloge display/query | 6 | 3 | 6 | 3 | 0%
* Filter datasets by time and space | 7 | 1 | 7 | 1 | 0%
* Export queried data | 8 | 4 | 8 | 4 | 0%
* Visualization | 6 | 3 | 6 | 3 | 0%
I. Snapshot (map) | 6 | 3 | 6 | 3 | 0%
II. Timeseries | 7 | 1 | 7 | 1 | 0%
III. Histograms | 8 | 4 | 8 | 4 | 0%
IV. Mutual trends (var1 vs var2) | 6 | 3 | 6 | 3 | 0%
V. Colocate variables with a 1-D trajectory | 6 | 3 | 6 | 3 | 0%